## Bugs
Id | Date | Status | Module | Description | Originator | Assignee | Priority | Estimate | Changelist
870 |  | Open | ALAM | Add pretest of devices | Wolff
460 | 2015-09-09 | Open | ALG | Remove hardcoded path from I-Frame | Wolff |  | 1
430 | 2015-08-18 | Open | ALTG | Add delete/purge Group capability | Wolff
990 |  | Open | DEV | Add tools dir to perforce | Wolff
1000 |  | Open | DEV | Relocate Perforce tree above Map Testing | Wolff
770 |  | Open | MAPBUN | Select map baseline cfg (for Trickle) according to Terminal version | Wolff |  | 1
810 |  | Open | MAPBUN | Remove old File Dowloads when starting Trickle | Wolff |  | 1
340 | 2015-08-13 | Open | MAPBUN | Update handling of Enable/Disable for Trickle Download configuration on NMS since may be other downloads | Wolff |  | 2
860 |  | Open | MAPBUN | Verify Term parameters before recon and reboot (for FLLock) | Wolff |  | 2
490 |  | Open | MAPBUN | Add Sysconfig for Hub Params such as Chip Rate | Wolff |  | 2
620 |  | Open | MAPBUN | Add checksum corner case fix to mapbunPrepFiles.sh | Wolff
820 |  | Open | MAPBUN | Support API for SGT Tool and collect errors | Wolff
830 |  | Open | MAPBUN | Create Datasheet Template | Wolff
1010 |  | Open | MAPBUN | Automatically generate Test Report | Wolff
840 |  | Open | NLG | Update naming to Data Collection | Wolff |  | 2
890 |  | Open | NLG | If NLG task dead in NlgConf then mark FALSE/0 | Wolff
920 |  | Open | NLG | Term Bug to not have section header IP Packet Receive, see Arclight-1453 | Wolff
940 |  | Open | NLG | VMT Command Beam Redirect; detect current beam switch to other beam (from hub1 and hub2 beams) | Wolff
1070 | 2016-02-29 | Open | REDA | Images do not load on webpage | Wolff
1080 | 2016-02-29 | Open | REDA | Colors/Contrasts are not dark and difficult to read | Wolff
1090 | 2016-02-29 | Open | REDA | Test scripts are not fully instrumented with test step progress | Wolff
1100 | 2016-02-29 | Open | REDA | performance .sql is not aligned with the latest REDA webpages. Needs updating, along with RedaLibrary.py API's to show results in ReDa | Wolff
500 |  | Open |  | Watchdog, for multiple groups simultaneously | Wolff |  | 2
10 | 2015-07-21 | Assigned | ALG | Batch GUI may have issue with Selenium Display conflict if another test launched | Wolff | Brent | 1
170 | 2015-07-22 | Assigned | ALTG | Support results dirs from any location and document rules, i.e. for httpd.conf | Wolff | Wolff | 3
60 | 2015-07-21 | Assigned | ALTG | Support Multiple Satellite Beam Names [Current workaround is to do 2 groups) | Wolff | Matt | 3
160 | 2015-07-22 | Assigned | Coords | Coords MATLAB should not protect against overwriting files (move existing to .BAK) | Wolff | Matt | 1
180 | 2015-07-21 | Assigned | Coords | Concentric Cirles on the Beam | Wolff | Matt | 2
100 | 2015-07-21 | Assigned | IT | Change DISPLAY from 47 to 142 | Wolff | Wolff | 3
410 | 2015-08-13 | Assigned | MAPBUN | Code Review/Audit Action Item - Add screenshots to include version and/ before/after | Wolff | Matt | 2
230 | 2015-08-12 | Assigned | MAPBUN | Add more captures to test cases | Wolff | Matt | 3
280 | 2015-08-13 | Assigned | MAPBUN | Add Reda calls for Progress and Pass/Fail | Wolff | Wolff | 3
380 | 2015-08-13 | Assigned | MYSQL | Code Review/Audit Action Item - Update mysql doc - %mysql performance --password, show tables; source <filename> | Wolff | Wolff | 2
290 | 2015-08-13 | Assigned | UTIL | Add Reda Screens | Wolff | Wolff | 3
260 | 2015-08-12 | Assigned | UTIL | Merge SSH and Serial Terminal, including SED_SSCF_Bundle.py with mapbun | Wolff | Wolff
700 | 2015-11-12 | In Progress | ALG | Fix VMT Fleet Commands for latest version | Wolff | Loutoo
1060 | 2015-07-21 | Closed | ALAM | Pass Fail Log | Wolff | Brent | 1
190 | 2015-08-13 | Closed | ALAM | Code Review/Audit Action Item - Fix all to upload w/reboot and get status version, Trickle, FL Lock, Precedence | Wolff | Matt | 2
420 |  | Closed | ALAM | Redefine Test type to mask and category | Wolff
520 | 2015-08-11 | Closed | ALDB | Combine redaConn and aldbConnConf | Wolff | Wolff | 1 |  | 1032243
210 | 2015-08-13 | Closed | ALDB | Optimize Get/Set pairs to allow Set(**Get()) | Wolff | Brent | 2
330 | 2015-09-09 | Closed | ALDB | Set Tuning Parameters defaults on Config Load | Wolff |  | 2
470 | 2015-12-16 | Closed | ALDB | Prevent new fields on terminal/nmspm VMT not in status database causing error; instead print warning | Wolff | Wolff
930 | 2015-10-01 | Closed | ALDB | Fix Terminal Status for multiple versions - ACU changes | Wolff
550 | 2015-10-01 | Closed | ALDB | Fix Terminal Status | Wolff
600 | 2015-08-17 | Closed | ALG | Add EFLM Tx Enable/Disable and incorporate into Precedence test and FL Lock & Trickle (Enable) | Wolff | Matt | 1
440 | 2015-07-14 | Closed | ALG | Screen Shot scroll | Wolff | Brent | 1
140 | 2015-08-13 | Closed | ALG | Code Review/Audit Action Item - See if Trickle correctly works, because GDRM version is displayed - ALREADY FIXED IN A NEWER VERSION OF VMT S/W | Wolff | Wolff | 2
400 | 2015-07-21 | Closed | ALG | ALG Wait on confversion complete | Wolff | Brent | 3
20 | 2015-12-16 | Closed | ALG | Need to Handle Terminal Hardware Type and the nuances associated thereof, e.g. sections different on MBR-4020 | Wolff | Wolff
910 | 2015-10-01 | Closed | ALG | Fix Terminal Status for multiple versions - ACU changes | Wolff | Wolff
560 | 2015-10-09 | Closed | ALG | Add VMT Fleet Commands | Wolff |  |  |  | 1056286
690 | 2015-07-21 | Closed | ALTG | Add Tuning Parameters, e.g. percents to screen/db/code | Wolff | Brent | 1
50 | 2015-08-13 | Closed | ALTG | Code Review/Audit Action Item - Add/update items to perforc, aldbDefaults, setEnv, MYSQL | Wolff | Wolff | 1
350 | 2015-08-13 | Closed | ALTG | Code Review/Audit Action Item - Config screen; lock config into results file, main screen as link at end, Link for Tuning Parameters | Wolff | Brent | 2
360 | 2015-08-13 | Closed | ALTG | Code Review/Audit Action Item - Tuning Screen, Keep tuning as a group or defaults, but get defaults from aldbDefaults (so tuning overrides on per group), change buttons to hyperlinks | Wolff | Brent | 2
370 | 2015-08-13 | Closed | ALTG | Combine test case columns on results screen | Wolff | Matt | 2
320 | 2015-07-22 | Closed | ALTG | Batch Environment does not use Apache Environment DISPLAY | Wolff | Brent | 2
150 | 2015-08-07 | Closed | ALTG | Group list into batch of tests | Wolff | Brent | 2
200 | 2015-07-21 | Closed | ALTG | Support Results | Wolff | Brent | 2
110 | 2015-08-13 | Closed | ALTG | Fix SAT?Beam naming | Wolff | Matt | 3
300 |  | Closed | ALTG | Option to regenerate a group | Wolff
431 |  | Closed | ALTG | Add RTNMS/Hub Mgmt Config Screen and use popup to select 1 and 2 in Main config | Wolff
961 |  | Closed | ALTG | Have lock remove files and regenerate | Wolff
432 |  | Closed | ALTG | Fix Summary/Description on Launch | Wolff
760 |  | Closed | ALTG | Show configuration summary on the Launch page | Wolff
761 | 2015-10-01 | Closed | ALTG | Add DB Export to GUI | Wolff | Loutoo
630 |  | Closed | ALTG | Fix Config Lock | Wolff
590 |  | Closed | ALTG | Create DB Export GUI prototype | Loutoo
640 |  | Closed | ALTG | Change Test Launch to Checkbox so that operator may select specific tests for execution | Wolff |  |  |  | 1056660
680 |  | Closed | ALTG | FL Rx Freq override for Tuning Parameter | Wolff
750 |  | Closed | ALTG | Change Hub in Tuning Parameters | Wolff
960 |  | Closed | Coords | Fix findAllCoords to generate single point for non-intersecting beam | Loutoo
530 |  | Closed | DEV | Get firefox working with Selenium on Test Auto VM | Wolff
1040 |  | Closed | DOC | Add /etc/ssh/ssh_known_hosts to SDD | Wolff
1020 |  | Closed | DOC | Add /usr/share/httpd group to apache for firefox | Wolff
1030 | 2015-07-21 | Closed | IT | Fix Test Server Reboot, e.g. iptable | Wolff | Wolff | 1
120 | 2015-07-21 | Closed | IT | Matlab Runtime Library Installation Procedure (Document) | Wolff | Matt | 1
40 | 2015-07-21 | Closed | MAPBUN | Support Dwell Time update in map by Change /test/sscf.csv on VMT to small value and reboot; adjust timing accordingly (For FL Lock and Precedence) AND /etc for MBR-4020 | Wolff | Wolff | 1
130 | 2015-07-21 | Closed | MAPBUN | If not existing, make as "None" /""/0 [Use a consistent rule for Pythoncomparison] | Wolff | Brent | 1
30 | 2015-07-21 | Closed | MAPBUN | Support both Signed and Unsiged Maps | Wolff | Wolff | 1
70 | 2015-08-10 | Closed | MAPBUN | Fix L-Band Rand to be within NMS/EFLM limits (lower and upper), and select antennas with single LO | Wolff | Wolff | 1
220 | 2015-08-12 | Closed | MAPBUN | Code Review/Audit | Wolff | Wolff | 1
270 | 2015-07-21 | Closed | MAPBUN | Support Polarization | Wolff | Wolff | 1
80 | 2015-07-21 | Closed | MAPBUN | Use SSCF for Satellite Beam Name and Validate | Wolff | Brent | 1
90 | 2015-09-09 | Closed | MAPBUN | Fix RF Freq selection based on transponder id in SED | Wolff |  | 2
450 | 2015-08-12 | Closed | MAPBUN | Check for version before changing to save time when doing Precedence and FLLock | Wolff | Matt
240 |  | Closed | MAPBUN | Precedence Verify a little buggy on repeating pattern therefore false errors; Fix Precedence verifications script; false failure on 6-8 th element when list repeats many times | Loutoo
510 |  | Closed | MAPBUN | Support Spectral Inversion | Wolff
580 |  | Closed | MAPBUN | map file checksum corner case | Loutoo
610 |  | Closed | MAPBUN | Fix beam selection | Wolff |  |  |  | 1059805
670 |  | Closed | MAPBUN | Fix Antenna Type for 200.x maps | Wolff |  |  |  | 1055811
710 | 2015-09-17 | Closed | MAPBUN | Fix MD5 Checksum extraction | Wolff |  |  |  | 1046746
720 |  | Closed | MAPBUN | Add MD5 Extraction to results | Wolff |  |  |  | 1046597
730 |  | Closed | MAPBUN | Re-write ALG Unit test as Class to support new NLG features | Wolff |  |  |  | 1045921
740 |  | Closed | MAPBUN | Fix FL Lock PASS/FAIL based on RF too so that correctly reports when Spectral Inversion | Wolff | Wolff
780 |  | Closed | MYSQL | Fix Terminal Status for multiple versions - add columns | Wolff
570 |  | Closed | NLG | Add VMT List summary Status to NMSPMStatusDB | Wolff |  | 1
850 |  | Closed | NLG | Support 2 hubs | Wolff |  | 2
880 | 2015-10-01 | Closed | NLG | Add syslog restrieval to NLG for both RTNMS and Terminal | Wolff | Wolff | 2
650 | 2015-11-11 | Closed | NLG | Add terminal only poll case | Wolff
660 |  | Closed | NLG | Add NLG to gather status in databases | Wolff
540 |  | Closed | NLG | Allow setting for Chart duration on NMSPM closeout | Wolff | Wolff
800 |  | Closed | NLG | Add script to post process the terminal syslog data | Wolff
970 |  | Closed | NLG | Add script to post process the rtnms syslog data | Wolff
980 | 2015-08-13 | Closed | UTIL | Code Review/Audit Action Item - VM documentation update, Snapshot & Load Icons; Datastore | Wolff |  | 2
390 | 2015-08-13 | Closed | UTIL | Tune timing 2/5/10 | Wolff | Wolff | 3
310 | 2015-08-12 | Closed | UTIL | Add SSH support for Terminal Com | Wolff | Brent
250 |  | Closed |  | Force a selection of status database on Export screen | Wolff | Wolff
900 |  | Closed |  | Fix association of Status Tag with Value (see Frederic eMail) | Wolff
1110 |  | Z |  |  | Wolff
1120 |  | Z |  |  | Wolff
1130 |  | Z |  |  | Wolff
1140 |  | Z |  |  | Wolff
1150 |  | Z |  |  | Wolff
1160 |  | Z |  |  | Wolff
1170 |  | Z |  |  | Wolff
1180 |  | Z |  |  | Wolff
1190 |  | Z |  |  | Wolff
1200 |  | Z |  |  | Wolff
1210 |  | Z |  |  | Wolff
1220 |  | Z |  |  | Wolff
1230 |  | Z |  |  | Wolff
1240 |  | Z |  |  | Wolff
1250 |  | Z |  |  | Wolff
1260 |  | Z |  |  | Wolff

## Accomplishments
Perforce
SDD as-built
SSDD as-built

## Goals
Map Bundle Test on ~ 8/10/2015